CHRONOLOGY REPORT

Operational Timeline & Evidence Log

Vessel: JOPETWIL 71 (IMO: 9582829)

Contract: SCT-19LT-PJC-LA-007 / OLCOF24-ALS086

Charter Party: SUPPLYTIME 2017 | Daily Hire: US$ 12,000

Owner: ADNOC Logistics & Services | Charterer: Samsung C&T Corporation

PERIOD COVERED: 26 February – 09 March 2026

STANDBY: D+10 (28 Feb – 09 Mar 2026)

Prepared by: Logistics Team – HVDC Project Office, Abu Dhabi

Date: 09 March 2026 | Document ID: JPT71-CHR-2026-001

CONFIDENTIAL – For Internal & Legal Use Only

Sources: WhatsApp Group "Jopetwil 71 Group" | WhatsApp Group "LCT Bushra" | Vessel Decklog

# 1. Purpose & Scope

본 Chronology Report는 JOPETWIL-71의 2026년 2월 26일 ~ 3월 9일 기간 운항 타임라인을 WhatsApp 그룹 채팅 로그 2건과 Decklog를 교차검증하여 작성한 공식 증빙 문서입니다. Clause 33 Lay-Up Request 및 Clause 35 Force Majeure Notice의 사실관계 근거로 활용됩니다.

Evidence Sources: (1) WhatsApp Group “Jopetwil 71 Group” — 선박 운항 지시/보고 | (2) WhatsApp Group “LCT Bushra” — Bushra/TR5 작업 및 AGI 통제 상황 | (3) Decklog_JOPETWIL71.xlsx — 선박 공식 항해일지

# 2. Legend

| CRITICAL | Standby/운항불가 직접 원인 — HM cast-off 금지, 보안사태, AGI 폐쇄 |
| --- | --- |
| WARNING | Berth 경합, 기상악화, 작업지연 — Standby 장기화 요인 |
| NORMAL | 정상 운항/작업 — 비교 기준점 |

# 3. Detailed Chronology

| # | Date/Time | Source | Event Description | Category | Contract Ref |
| --- | --- | --- | --- | --- | --- |
| PHASE 1: 정상 운항 (Normal Operations) — Feb 26~27 |  |  |  |  |  |
| 1 | 02.26 15:45 | JPT71 Chat | MW4 cargo loading completed (9 trucks, ≈700t aggregate 20mm) | Operation | — |
| 2 | 02.26 18:00 | JPT71 Chat | Vessel secured at JPT Jetty for shelter. Weather standby begins. | Weather | Cl.13(a)(iv) |
| 3 | 02.27 07:52 | JPT71 Chat | 상욱: Cast off instruction — “Once Bushra complete, will berth at Jetty #3” | Instruction | — |
| 4 | 02.27 08:42 | Bushra Chat | LCT Bushra cast off from Mina Zayed. ETA AGI 2100hrs. | Bushra Ops | — |
| 5 | 02.27 19:42 | Bushra Chat | Bushra drop anchor at Al Ghallan anchorage. | Bushra Ops | — |
| PHASE 2: Bushra AGI Berth 점유 & 보안사태 (Feb 28) |  |  |  |  |  |
| 6 | 02.28 07:12 | Bushra Chat | LCT BUSHRA secured A/S at AGI berth no 3. → JPT71 berth 차단 | Berth Blocked | Cl.33 trigger |
| 7 | 02.28 11:20 | JPT71 Chat | Sajid: “No, LCT Bushra TR offloading in progress... Today is not possible.” | Berth Denied | Cl.13(a)(vi) |
| 8 | 02.28 11:27 | JPT71 Chat | Sajid: “Tomorrow all site activities are closed as per ADNOC Instructions.” Bushra standby on Jetty #3. | ADNOC Shutdown | Cl.35(b) |
| 9 | 02.28 16:06 | Bushra Chat | Yulia MAMMOET: “Due to security situation requesting to release MMT crew from Al Ghallan Island.” | Security Alert | Cl.35(a)(b)(c) |
| 10 | 02.28 16:13 | Bushra Chat | All outdoor work has been stopped. AGI team waiting further instruction from ADNOC. | Site Closure | Cl.35(b) |
| 11 | 02.28 19:23 | JPT71 Chat | JPT71 at Zakum anchorage, awaiting instructions. No berth available. | Standby | Hire continues |
| PHASE 3: JPT71 Shelter 이동 & Standby 장기화 (Mar 1~5) |  |  |  |  |  |
| 12 | 03.01 10:40 | JPT71 Chat | Captain Henok: “Permission to proceed to JPT jetty for shelter — weather getting bad, AGI port also closed.” → 상욱: “Yes ok, proceed.” | Shelter Move | Cl.13(a)(iv) |
| 13 | 03.02 11:10 | Bushra Chat | 상욱: “4th TR offloaded around 1600... Pls request berthing in MZP or another berth.” → Weather forecast: waiting till 6th Mar. | Berth Search | — |
| 14 | 03.02 11:21 | Bushra Chat | Port not allowing berth for layby in MZ and Freeport. MZ berth occupied. | All Berths Denied | Cl.35(b) |
| 15 | 03.02 18:54 | Bushra Chat | AGI Harbour Master: Bushra cast off or sailing under his instruction only — vessel status as standby for personnel evacuation. | HM Detention | Cl.35(b) govt control |
| 16 | 03.02 19:03 | Bushra Chat | 상욱: “SCT in ongoing discussion with AGI ADNOC — obligated to follow ADNOC Evacuation Plan.” | Evacuation | Cl.35(b) |
| 17 | 03.03 07:42 | JPT71 Chat | 상욱: “Possible castoff on 8th Mar.” Captain: “As per forecast possible 8th Mar 1800hrs.” | Forecast | Cl.13(a)(iv) |
| 18 | 03.03 07:55 | Bushra Chat | Bushra: “Still waiting for instructions from HM, vessel standby.” Weather not good for transit. | HM Hold | Cl.35(b) |
| PHASE 4: AGI Cast-off 전면 금지 & 해제 불가 (Mar 6~9) |  |  |  |  |  |
| 19 | 03.06 09:31 | Bushra Chat | MZ berth is still occupied. “When are we planning next TR loading?” → “Once berth available.” | MZ Blocked | No alt berth |
| 20 | 03.06 07:37 | JPT71 Chat | 상욱: Check weather + FW supply. Berthing request for 8 Mar submitted. | Planning | — |
| 21 | 03.07 07:54 | Bushra Chat | No vessel allowed cast off Al Ghallan except for urgent cargo. All LCTs detained. | CAST-OFF BAN | Cl.35(b) govt interv. |
| 22 | 03.07 10:07 | Bushra Chat | ADNOC Ouda: “Who is stopping vessel? Vessel standby since 02 March 19:00.” Bushra: “HM instruct us to standby.” | HM Confirmed | Cl.35(b) |
| 23 | 03.07 11:02 | JPT71 Chat | Sajid: “If JPT71 reach AGI, remain at Anchorage until Bushra cast off from Jetty #3.” | Berth Blocked | Hire continues Cl.13(a)(iv)(vi) |
| 24 | 03.07 11:08 | JPT71 Chat | Ship Master: “Better to stay at ICAD until AGI resume cargo operation and fully operational.” | Ops Suspended | Full standby |
| 25 | 03.07 14:46 | Bushra Chat | ADNOC Ouda: “Shipping will advise if they can substitute Bushra for emergency response.” | Resolution | — |
| 26 | 03.08 17:17 | Bushra Chat | ADNOC Ouda: “There is no replacement vessel for Bushra till the moment.” | NO RESOLUTION | Standby indefinite |
| 27 | 03.08 21:26 | Bushra Chat | “Any update on vessel ETA to MZ?” → “No updates yet.” | No Progress | — |
| 28 | 03.09 — | Analysis | D+10 Standby. Cumulative hire: US$ 120,000. Clause 33 Lay-Up Request 발송 결정. | ACTION | Cl.33(a) Cl.35 notice |

# 4. Key Findings & Contract Implications

| Finding | Evidence (WhatsApp) | Contract Implication |
| --- | --- | --- |
| AGI Cast-off 전면 금지 | “No vessel allowed cast off except urgent cargo” (Mar 7, Bushra) | Cl.35(b) government control/intervention → FM 요건 충족 |
| Bushra HM 강제 억류 | “Cast off under HM instruction only, standby for evacuation” (Mar 2, Bushra) | Cl.35(b) → Bushra 해제불가 → JPT71 berth 부재 |
| 보안사태 / ADNOC Shutdown | “All outdoor work stopped” + “Security situation” (Feb 28, Bushra) | Cl.35(a)(b)(c) acts of God / govt intervention / war-like acts |
| 기상악화 장기화 | Multiple “no sailing” / “weather bad” entries (Feb 14, 16, Mar 1, 3) | Cl.13(a)(iv) stress of weather → Charterer account, hire continues |
| MZ 대체 Berth 불가 | “Port not allowing berth for layby in MZ and Freeport” (Mar 2) + “MZ still occupied” (Mar 6) | 모든 대체 berth 소진 → JPT71 Jetty shelter 외 선택지 없음 |
| ADNOC 대체선 불가 | “No replacement vessel for Bushra till the moment” (Mar 8, ADNOC Ouda) | 해제 시점 미정 → Lay-Up 전환 불가피 |

# 5. Standby Cost Accumulation

| Day | Date | Status | Daily Hire | Cumulative | VAT 5% | Total |
| --- | --- | --- | --- | --- | --- | --- |
| D+1 | 02.28 | Standby | $12,000 | $12,000 | $600 | $12,600 |
| D+2 | 03.01 | Shelter | $12,000 | $24,000 | $1,200 | $25,200 |
| D+3 | 03.02 | Shelter | $12,000 | $36,000 | $1,800 | $37,800 |
| D+4 | 03.03 | Shelter | $12,000 | $48,000 | $2,400 | $50,400 |
| D+5 | 03.04 | Shelter | $12,000 | $60,000 | $3,000 | $63,000 |
| D+6 | 03.05 | Shelter | $12,000 | $72,000 | $3,600 | $75,600 |
| D+7 | 03.06 | Shelter | $12,000 | $84,000 | $4,200 | $88,200 |
| D+8 | 03.07 | Shelter | $12,000 | $96,000 | $4,800 | $100,800 |
| D+9 | 03.08 | Shelter | $12,000 | $108,000 | $5,400 | $113,400 |
| D+10 | 03.09 | Shelter | $12,000 | $120,000 | $6,000 | $126,000 |

# 6. Conclusion

WhatsApp 로그 증빙에 기반한 사실관계 요약:

(1) JOPETWIL-71은 2026.02.28부터 운항 불가 상태이며, 그 원인은 전적으로 외부요인(AGI HM cast-off 금지, 보안사태, 기상악화, berth 점유)입니다.

(2) Bushra는 AGI Harbour Master의 강제 억류 하에 대피 선박으로 묶여 있으며, ADNOC은 대체선을 확보하지 못했습니다 (Mar 8 확정).

(3) MZ 및 Freeport berth도 점유/통제로 사용 불가하여 모든 대체 경로가 차단되었습니다.

(4) 계약상 Off-Hire는 불성립이며 (Cl.13(a) 예외), Charter Hire US$ 12,000/day가 계속 발생 중입니다.

(5) Clause 33 Lay-Up 전환이 유일하게 실효적인 비용절감 수단이며, FM Notice로 권리를 보전해야 합니다.

본 문서의 WhatsApp 발취문은 원문 그대로 인용하였으며, 변경/편집되지 않았음을 확인합니다. 원본 로그는 별도 보관됩니다.