CONFIDENTIAL

March 9, 2026

ADNOC Logistics & Services (ALS)

P.O. Box 898, Abu Dhabi

United Arab Emirates

Attention: Chartering & Marine Operations Department

Re: FORMAL NOTICE OF FORCE MAJEURE EVENT

Charter Party: SCT-19LT-PJC-LA-007 / OLCOF24-ALS086

Vessel: JOPETWIL 71

Form: SUPPLYTIME 2017 (BIMCO)

Dear Sirs,

# 1. NOTICE OF FORCE MAJEURE

We write on behalf of Samsung C&T Corporation ("Charterers") to formally notify ADNOC Logistics & Services ("Owners") of the occurrence of Force Majeure events pursuant to Clause 35 (Force Majeure) of the Charter Party referenced above.

This notice is issued within the five (5) day written notice period prescribed by Clause 35, paragraph 2, which states: "The party seeking to invoke force majeure shall notify the other party in writing within five (5) days of the occurrence of any such event/condition."

# 2. FACTUAL BACKGROUND

On 27 February 2026, the Vessel LCT Bushra cast off from Mina Zayed carrying equipment for the HVDC Interconnector Project and arrived at Al Ghallan Island (AGI) anchorage on the same day. The Vessel secured alongside AGI Berth No. 3 on 28 February 2026 at 0712 hrs.

On the afternoon of 28 February 2026, a security situation was declared at Al Ghallan Island. ADNOC issued directives to stop all outdoor work and placed all project teams on standby. ADNOC's own teams and Samsung C&T teams were actively seeking evacuation options. The Vessel was designated as a potential evacuation vessel.

From 2 March 2026 onwards, the AGI Harbour Master issued a cast-off prohibition, stating the Vessel may only depart "under his instruction only" as it was placed on standby for personnel evacuation. This prohibition has remained in effect continuously. On 7 March 2026, the Harbour Master confirmed: "No vessel allowed cast off Al Ghallan except for urgent cargo."

Additionally, during this period, extraordinary weather conditions further prevented any vessel transit, with weather reports confirming conditions were "not good enough for transit with any passenger."

On 8 March 2026, ADNOC confirmed that no replacement vessel is available for LCT Bushra, meaning the JOPETWIL 71 operations remain completely suspended with no alternative means of performance.

# 3. FORCE MAJEURE GROUNDS UNDER CLAUSE 35

The events described above constitute Force Majeure under the following sub-clauses of Clause 35:

## 3.1 Clause 35(a) — Acts of God

Extraordinary weather conditions during the standby period rendered vessel transit unsafe. Weather reports from 1–3 March 2026 confirmed deteriorated sea states that were "not good enough for transit with any passenger." These conditions are beyond the reasonable control of either party.

## 3.2 Clause 35(b) — Government Requisition, Control, Intervention

The AGI Harbour Master’s cast-off prohibition constitutes direct government control and intervention over the Vessel’s movement. This is not a commercial decision but a mandatory regulatory directive from the port authority, acting under ADNOC’s overall security and evacuation framework. The Vessel has been effectively requisitioned for standby evacuation purposes since 2 March 2026.

Furthermore, ADNOC’s shutdown of all outdoor operations at AGI and placement of all personnel on standby constitutes government-level intervention that has prevented performance of charterer’s operations.

## 3.3 Clause 35(c) — War, Threatened Act of War, Acts of Terrorism

The "security situation" declared at Al Ghallan Island on 28 February 2026, which triggered the ADNOC shutdown, evacuation protocols, and the Harbour Master’s vessel detention order, falls within the scope of circumstances arising out of threatened acts of war or acts of terrorism, or the consequences thereof. The nature of the security alert necessitated personnel evacuation and designation of LCT Bushra for emergency response.

## 3.4 Clause 35(d) — Blockades or Embargoes

The Harbour Master’s blanket prohibition on vessel movements at Al Ghallan Island — "No vessel allowed cast off" — constitutes a de facto blockade of all maritime traffic in and out of AGI, preventing the Vessel from performing its chartered service.

## 3.5 Clause 35(f) — Extraordinary Weather Conditions

As noted above, extraordinary weather conditions during the period from 1 to 5 March 2026 independently constituted a Force Majeure event by preventing safe navigation. These weather conditions, compounding the security-related detention, further delayed and hindered performance.

# 4. MITIGATION EFFORTS

In accordance with the requirement under Clause 35 that the invoking party shall have "made all reasonable efforts to avoid, minimize or prevent the effect of such events," the Charterers confirm the following mitigation steps have been undertaken:

- Requested alternative berthing at Mina Zayed, RORO jetty, LMS base, Al Jaber, and MW4 facilities to relocate the Vessel from AGI and resume operations (2 March 2026);

- Obtained Samsung management approval for Vessel to proceed to LMS base for provisioning and layby (2 March 2026);

- Coordinated with ADNOC (Eng. OUDA) to negotiate Vessel release from AGI Harbour Master detention (2–7 March 2026);

- Requested ADNOC Shipping to provide a substitute vessel to release LCT Bushra (7–8 March 2026);

- Continuously monitored berth availability at Mina Zayed and alternative ports (3–9 March 2026);

- Checked tidal windows for next Transformer loading operation to ensure minimal delay upon Vessel release (6 March 2026);

# 5. IMPACT ON CHARTER PARTY PERFORMANCE

As a direct consequence of the above Force Majeure events, the Charterers have been prevented and hindered from performing the following obligations under the Charter Party:

- Loading and transport of Transformer Unit No. 5 (5th of 6 total units) from Mina Zayed to AGI;

- Return of LCT Bushra to Mina Zayed for deck preparation and cargo loading operations;

- Completion of remaining project transport schedule within the charter period ending 31 March 2026;

The Vessel has been on involuntary standby at AGI since 2 March 2026, accumulating daily hire charges of US$ 12,000 (per Amendment No. 1) without any productive utilization. As of 9 March 2026, the cumulative cost impact of the FM-related standby period is US$ 96,000 (8 days × US$ 12,000/day), excluding applicable VAT.

# 6. RELIEF SOUGHT

By this notice, the Charterers seek the following relief in connection with the Force Majeure events:

(a) Acknowledgment by Owners that the events described herein constitute Force Majeure under Clause 35;

(b) Release from liability for any loss, damage, or delay arising from the Force Majeure period in accordance with Clause 35;

(c) Good faith discussion regarding the equitable treatment of hire charges during the period the Vessel is detained by Force Majeure events beyond the Charterers' control, noting that Clause 13(a) off-hire provisions do not provide relief in FM scenarios;

(d) Cooperation in securing the Vessel's earliest possible release from AGI to resume chartered operations.

# 7. RESERVATION OF RIGHTS

This Notice is issued without prejudice to any and all rights and remedies available to the Charterers under the Charter Party, at law, or in equity, including but not limited to:

- Rights under Clause 33 (Lay-Up) — a separate notice regarding Lay-Up has been issued concurrently;

- Rights under Clause 14(b) (Excluded Losses) regarding consequential losses;

- Rights under UAE Civil Code Article 249 regarding equitable adjustment of contractual obligations due to exceptional and unforeseen circumstances;

- Rights under Additional Clause 43 (ICC Arbitration, Abu Dhabi seat) should dispute resolution become necessary.

# 8. ENCLOSURES

The following documents are enclosed in support of this Force Majeure Notice:

Enclosure 1: Chronology Report — Detailed timeline of FM events based on operational communications (28 Feb – 9 Mar 2026)

Enclosure 2: WhatsApp operational logs — JOPETWIL 71 Group & LCT Bushra Group (source evidence)

Enclosure 3: Charter Party Cost Analysis Report (ref: JOPETWIL71_Charter_Cost_Analysis_20260309)

We request your prompt acknowledgment of this Notice and look forward to your cooperation in resolving this matter in accordance with the terms of the Charter Party.

This Notice shall be deemed effective as of the date first written above.

Yours faithfully,

For and on behalf of

SAMSUNG C&T CORPORATION

Engineering & Construction Group

_______________________________

Authorized Signatory

Project Logistics / SCM Department

HVDC Interconnector Project

cc:

Samsung C&T — Project Director, HVDC Interconnector

Samsung C&T — Contract Manager

Samsung C&T — SCM HQ, Seoul

Samsung C&T — Legal Department

ANNEX A: CHRONOLOGY OF FORCE MAJEURE EVENTS

28 February 2026 – 9 March 2026

| # | Date | Event Description | Clause Ref | Category |
| --- | --- | --- | --- | --- |
| 1 | 28 Feb 2026 | ADNOC issues shutdown directive; all outdoor work stopped at AGI due to "security situation" | Cl.35(b)(c) | CRITICAL |
| 2 | 28 Feb 2026 | SCT requests Mammoet crew evacuation from Al Ghallan Island | Cl.35(b)(c) | CRITICAL |
| 3 | 28 Feb 2026 | All Project Lightning teams placed on standby per ADNOC instruction | Cl.35(b) | CRITICAL |
| 4 | 02 Mar 2026 | AGI Harbour Master prohibits vessel cast-off: "under his instruction only" — vessel designated standby for personnel evacuation | Cl.35(b)(d) | CRITICAL |
| 5 | 02 Mar 2026 | Mammoet crew boards LCT Bushra without authorization amid evacuation uncertainty | Cl.35(b)(c) | WARNING |
| 6 | 03 Mar 2026 | Vessel remains on standby at AGI; weather conditions deteriorate — "not good enough for transit with any passenger" | Cl.35(a)(f) | CRITICAL |
| 7 | 07 Mar 2026 | AGI HM confirms: "No vessel allowed cast off Al Ghallan except for urgent cargo" | Cl.35(b)(d) | CRITICAL |
| 8 | 07 Mar 2026 | ADNOC Shipping unable to provide replacement vessel; LCT Bushra remains detained at AGI | Cl.35(b) | CRITICAL |
| 9 | 08 Mar 2026 | ADNOC confirms: "No replacement vessel for Bushra till the moment" | Cl.35(b) | CRITICAL |

Legend:

| CRITICAL | Events directly preventing charter performance; regulatory/security-imposed |
| --- | --- |
| WARNING | Events contributing to FM situation; operational complications |

Source: WhatsApp operational communications — JOPETWIL 71 Group & LCT Bushra Group. Full chronology available in Enclosure 1 (Chronology Report).

--- End of Annex A ---