| DATE | 9 March 2026 |
| --- | --- |
| FROM | Project Logistics / SCM Department |
| TO | Project Director, HVDC Interconnector |
| CC | Contract Manager / SCM HQ Seoul / Legal Dept. |
| SUBJECT | JOPETWIL 71 — Standby Situation UPDATE #2: FM Notice Issued |
| PRIORITY | URGENT — ACTION REQUIRED |
| CLASSIFICATION | CONFIDENTIAL |

# 1. EXECUTIVE SUMMARY

FORCE MAJEURE NOTICE ISSUED Clause 35 FM Notice formally dispatched to ADNOC L&S (Owner) on 9 March 2026, citing 5 grounds: acts of God, government control, security/terrorism consequences, de facto blockade, and extraordinary weather. Vessel detained at AGI since 2 March; cumulative standby cost US$ 96,000 (D+8). Concurrent Clause 33 Lay-Up Request also issued to negotiate hire reduction.

# 2. SITUATION UPDATE SINCE MEMO #1

## 2.1 Key Developments (9 March 2026)

(a) Clause 35 Force Majeure Notice — Formal written notice dispatched to ALS invoking FM under 5 sub-clauses (a)(b)(c)(d)(f). Notice cites the 5-day statutory deadline and includes Chronology Report as enclosure. Relief sought: FM acknowledgment, liability release, equitable hire discussion, and cooperation for vessel release.

(b) Chronology Report completed — 28 events across 4 phases compiled from WhatsApp operational logs (JOPETWIL 71 Group + LCT Bushra Group). Color-coded by severity. Provides evidentiary foundation for FM and potential arbitration.

(c) AGI HM cast-off ban remains in force — As of 9 March, "No vessel allowed cast off Al Ghallan except for urgent cargo" (confirmed 7 March). ADNOC also confirmed "No replacement vessel for Bushra" (8 March). Vessel remains involuntarily idle.

(d) Lay-Up Rate Scenario Analysis — 9-discount-rate interactive model completed (30%–70% reduction). Break-even analysis shows Lay-Up becomes cost-effective at ~40% discount with 3-day lead time. Strongest negotiation leverage: Cl.35 FM + UAE Civil Code Art. 249 hardship doctrine.

## 2.2 Vessel & Cargo Status

| Vessel | JOPETWIL 71 (LCT Bushra) |
| --- | --- |
| Current Location | Al Ghallan Island, Berth No. 3 |
| Status | INVOLUNTARY STANDBY — FM Event |
| Detained Since | 2 March 2026 (D+8 as of today) |
| Daily Hire | US$ 12,000/day (Amend. No.1) |
| Cumulative Standby Cost | US$ 96,000 (excl. VAT) |
| Next Cargo | Transformer Unit No. 5 (5th of 6) |
| Cargo Location | Mina Zayed — awaiting vessel return |
| Charter Expiry | 31 March 2026 (22 days remaining) |

# 3. COST IMPACT ANALYSIS

| Period | Dates | Period Cost | Cumulative | FM Trigger |
| --- | --- | --- | --- | --- |
| D+1 to D+3 | 2-4 Mar | US$ 36,000 | US$ 36,000 | Security + Weather |
| D+4 to D+6 | 5-7 Mar | US$ 36,000 | US$ 72,000 | HM Cast-off Ban |
| D+7 to D+8 | 8-9 Mar | US$ 24,000 | US$ 96,000 | No Replacement |
| D+9 to D+22 | 10-31 Mar | US$ 168,000 | US$ 264,000 | Projected if unresolved |

Worst-case total exposure (if vessel remains detained through charter expiry): US$ 264,000 + 5% VAT = US$ 277,200

# 4. ACTIONS COMPLETED

| # | Action Item | Owner | Status |
| --- | --- | --- | --- |
| 1 | Charter Party full contract analysis (English + Korean) | SCM | DONE |
| 2 | COST-GUARD 3-option dashboard (Lay-Up vs Standby vs Termination) | SCM | DONE |
| 3 | Clause 33 Lay-Up Request letter issued to ALS | SCM | DONE |
| 4 | Lay-Up Rate Scenario comparison (9 rates, interactive) | SCM | DONE |
| 5 | Internal Summary Memo #1 distributed | SCM | DONE |
| 6 | WhatsApp evidence compiled & analyzed (2 groups, 600+ messages) | SCM | DONE |
| 7 | Chronology Report (28 events, 4 phases) | SCM | DONE |
| 8 | Clause 35 Force Majeure Notice issued to ALS | SCM/Legal | DONE |
| 9 | Internal Summary Memo #2 (this document) | SCM | DONE |

# 5. IMMEDIATE ACTIONS REQUIRED

| # | Action Required | Owner | Deadline | Priority |
| --- | --- | --- | --- | --- |
| 1 | Secure PD/CM signature on FM Notice and dispatch to ALS | Legal/SCM | 10 Mar | URGENT |
| 2 | Follow up with ALS for FM acknowledgment (5-day response) | SCM | 14 Mar | URGENT |
| 3 | Begin hire reduction negotiation under Cl.33 + Art.249 | Contract Mgr | 12 Mar | HIGH |
| 4 | Coordinate with ADNOC for vessel release from AGI HM | SCM/ADNOC | Ongoing | HIGH |
| 5 | Prepare arbitration brief if Owner rejects FM + Lay-Up | Legal | 20 Mar | MEDIUM |
| 6 | Update cost model daily and circulate weekly KPI dashboard | SCM | Weekly | MEDIUM |

# 6. RISK REGISTER

| # | Risk Description | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- | --- |
| R1 | Owner rejects FM claim entirely | HIGH | HIGH | Escalate to ICC Arbitration (Cl.43); UAE Civil Code Art. 249 hardship argument as fallback |
| R2 | Vessel detained beyond charter expiry (31 Mar) | MEDIUM | CRITICAL | Exercise Cl.33 Lay-Up immediately to reduce hire; negotiate extension only if FM resolved |
| R3 | Transformer No.5 delivery delayed >30 days | HIGH | HIGH | Explore alternative vessel; inform client (ADNOC Power) of revised schedule |
| R4 | ALS claims hire continues under Cl.13(a) off-hire exceptions | HIGH | HIGH | Counter with FM doctrine (Cl.35 is separate mechanism); cite blockade/govt control as distinct from Cl.13 scenarios |
| R5 | Security situation escalation at AGI | LOW | CRITICAL | Activate emergency evacuation plan; prioritize crew safety over commercial considerations |

# 7. DELIVERABLES INVENTORY

All documents prepared and available for distribution:

| # | Document | Description | Status |
| --- | --- | --- | --- |
| 1 | Charter_Cost_Analysis.docx | Full contract analysis (English) | READY |
| 2 | 차터비용_보상분석.docx | Contract analysis (Korean) | READY |
| 3 | COST_GUARD_3Option.html | Lay-Up vs Standby vs Termination dashboard | READY |
| 4 | Clause33_LayUp_Request.docx | Formal Lay-Up Request letter to ALS | READY |
| 5 | LayUp_Rate_Scenarios.html | 9-rate scenario comparison dashboard | READY |
| 6 | Internal_Summary_#1.docx | First internal summary memo | SENT |
| 7 | Chronology_Report.docx | 28-event FM evidence timeline | READY |
| 8 | FM_Notice_Clause35.docx | Formal Force Majeure Notice to ALS | READY |
| 9 | Internal_Summary_#2.docx | This document (updated situation report) | READY |

# 8. CRITICAL TIMELINE

| Date | Milestone | Owner | Status |
| --- | --- | --- | --- |
| 28 Feb | Security situation declared at AGI; ADNOC shutdown | ADNOC | DONE |
| 2 Mar | HM cast-off ban; vessel detained for evacuation standby | AGI HM | DONE |
| 7 Mar | Full cast-off prohibition confirmed; no replacement vessel | AGI HM | DONE |
| 9 Mar | FM Notice + Lay-Up Request + Chronology Report completed | SCM | TODAY |
| 10 Mar | FM Notice dispatch with PD/CM signature to ALS | SCM/Legal | PENDING |
| 12 Mar | Initiate hire reduction negotiation (Cl.33 + Art.249) | Contract Mgr | PENDING |
| 14 Mar | ALS FM response deadline (5 days from dispatch) | ALS | PENDING |
| 17 Mar | Lay-Up Owner response deadline (7 days from notice) | ALS | PENDING |
| 20 Mar | Decision gate: arbitration brief if no resolution | Legal | PENDING |
| 31 Mar | Charter expiry — final cost settlement | All | PENDING |

# 9. LEGAL STRATEGY SUMMARY

The dual-track approach (FM Notice + Lay-Up Request) is designed to maximize Samsung C&T's negotiation position:

Track 1 — Clause 35 FM Notice: Establishes legal record that the standby is caused by force majeure events beyond Charterer’s control. Even though Cl.35 does not suspend hire (per Cl.13(a)), it shields against liability claims and forms the basis for equitable relief under UAE Civil Code Art. 249.

Track 2 — Clause 33 Lay-Up Request: Triggers the contractual mechanism for hire reduction during periods of vessel non-utilization. Combined with FM grounds, creates compelling case for Owner to agree to reduced rate during detention period.

Fallback — ICC Arbitration: If Owner rejects both FM and Lay-Up, Additional Clause 43 provides for ICC arbitration in Abu Dhabi. The Chronology Report and WhatsApp evidence provide strong evidentiary foundation. UAE courts are generally receptive to Art. 249 hardship arguments.

This memo supersedes Internal Summary #1 dated 9 March 2026. Next update will be issued upon receipt of Owner’s response to the FM Notice or upon material change in vessel status.

Respectfully submitted,

Project Logistics / SCM Department

Samsung C&T Corporation

HVDC Interconnector Project