JPT71 HVDC PROJECT

Voyage Cost Reconciliation Report

v5.3 — Comprehensive Analysis

Samsung C&T Corporation · Project Logistics Division

ADNOC Offshore HVDC Interconnection Project

Period: July 2024 – February 2026 (19 Months)

Report Date: 10 March 2026

Prepared by: MACHO-GPT v5.3 / Project Logistics Analytics

# 1. Executive Summary

This report provides a comprehensive reconciliation and cost analysis of vessel logistics operations for the JPT71 HVDC Interconnection Project (ADNOC Offshore). The analysis covers 19 months of operations (July 2024 through February 2026), integrating three sub-contractor cost streams: OFCO (vessel time charter operations), Global Maritime (GM, marine survey services), and ALS (charter hiring).

## Key Performance Indicators

| Metric | Value | Unit | Note |
| --- | --- | --- | --- |
| Total Integrated Cost | 27,480,131 | AED | OFCO+GM+ALS |
| Total Tonnage (Reconciled) | 64,641 | metric tons | OFCO voyages |
| Blended Cost Rate | 314.67 | AED/ton | All-in rate |
| Total Voyages | 106 | voyages | OFCO matched |
| Operating Period | 19 | months | Jul 2024 – Feb 2026 |
| ALS Cost Share | 78.7% | of total | Fixed cost dominant |

Critical Finding: ALS charter hire constitutes 78.7% of total project logistics cost (AED 21.6M of 27.5M) as a fixed monthly expense averaging AED 1.14M/month. Monthly tonnage variation is the primary driver of cost efficiency, with AED/ton ranging from 130.5 (Sep 2024, 12,388t) to 1,257.5 (Feb 2025, 1,282t).

# 2. Scope and Methodology

## 2.1 Data Sources

- JPT-reconciled_v5.3.xlsx: Master workbook with 12 sheets — OFCO invoices (1,304 line items), voyage records (133 voyages), decklog (382 operational days), and integrated cost allocations

- 기성.xlsx (Progress Payment): 57 invoices across 3 sub-contractors (OFCO, GM, ALS) with 92 GRM voyage records for GM allocation mapping

- DECKLOG data: 382 operational day records (post ADNOC 225 exclusion) covering fuel consumption, vessel activities, and port operations

## 2.2 Allocation Methodology

OFCO: Direct invoice-to-voyage matching using Voyage ID cross-referencing. 1,031 direct matches + 37 prorate-applied + 34 multi-prorated line items. Classification system (CLS_TYPE) tags each line as DIRECT, PRORATE_APPLIED, MULTI_PRORATED, BUSHRA_EXCLUDED, or JUMBOBAG.

GM (Global Maritime): Invoice → grm_voyage mapping → tonnage-prorated allocation across voyages within each invoice batch. 12 invoices → 92 voyage allocations. Coverage: 98.8% (AED 598,986 of 606,148). One unmatched invoice AD_0010625 (AED 7,161).

ALS (Charter Hiring): Supply month → ALL voyages (GRM + SCT) in that month → tonnage-prorated allocation. 21 invoices → 154 voyage allocations. Coverage: 100.0%. Key correction: used VOYAGE sheet (all 133 voyages) instead of grm_voyage (92 GRM-only) to capture SCT voyages in Feb–Mar 2025.

# 3. Cost Breakdown by Sub-Contractor

| Sub-Contractor | Total AED | Share % | Cost Type | Rate |
| --- | --- | --- | --- | --- |
| ALS (Charter) | 21,637,319 | 78.7% | Fixed | ~1.14M/mo |
| OFCO (Vessel Ops) | 5,243,825 | 19.1% | Variable | 81.12/ton |
| GM (Survey) | 598,986 | 2.2% | Semi-variable | 9.83/ton |
| TOTAL | 27,480,131 | 100.0% | — | 314.67/ton |

The cost structure reveals a heavily fixed-cost dominated profile. ALS charter hire at AED 21.6M represents nearly 4x the OFCO variable costs. This structural imbalance means that voyage density (monthly tonnage throughput) is the single most impactful lever for reducing the blended AED/ton rate.

# 4. Monthly Integrated Cost Analysis

| Month | Voy | Ton | ALS | OFCO | GM | Total | AED/t | ALS% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 2024-07 | 2 | 2,446 | 821,178 | 9,674 | 19,594 | 850,446 | 347.7 | 97% |
| 2024-08 | 10 | 6,066 | 1,138,475 | 322,965 | 65,483 | 1,526,923 | 251.7 | 75% |
| 2024-09 | 10 | 12,388 | 1,118,174 | 436,059 | 62,876 | 1,617,109 | 130.5 | 69% |
| 2024-10 | 8 | 4,095 | 1,138,475 | 320,802 | 30,777 | 1,490,054 | 363.9 | 76% |
| 2024-11 | 6 | 3,361 | 1,101,750 | 266,026 | 30,611 | 1,398,387 | 416.1 | 79% |
| 2024-12 | 9 | 10,532 | 1,421,258 | 265,199 | 51,169 | 1,737,625 | 165.0 | 82% |
| 2025-01 | 4 | 1,932 | 1,308,585 | 31,740 | 12,487 | 1,352,812 | 700.3 | 97% |
| 2025-02 | 6 | 1,282 | 1,233,960 | 378,194 | 0 | 1,612,154 | 1257.5 | 77% |
| 2025-03 | 4 | 2,308 | 1,366,170 | 199,848 | 0 | 1,566,018 | 678.5 | 87% |
| 2025-04 | 6 | 3,013 | 1,322,100 | 371,130 | 17,911 | 1,711,141 | 567.9 | 77% |
| 2025-05 | 4 | 2,931 | 991,134 | 269,638 | 25,792 | 1,286,564 | 438.9 | 77% |
| 2025-07 | 5 | 3,639 | 776,513 | 291,332 | 30,741 | 1,098,587 | 301.9 | 71% |
| 2025-08 | 5 | 2,390 | 1,156,838 | 560,781 | 12,962 | 1,730,580 | 724.0 | 67% |
| 2025-09 | 8 | 6,095 | 1,322,100 | 559,534 | 57,808 | 1,939,442 | 318.2 | 68% |
| 2025-10 | 9 | 6,429 | 1,366,170 | 289,888 | 57,160 | 1,713,217 | 266.5 | 80% |
| 2025-11 | 9 | 5,360 | 1,322,100 | 191,763 | 37,979 | 1,551,842 | 289.5 | 85% |
| 2025-12 | 9 | 5,813 | 1,366,170 | 245,930 | 26,235 | 1,638,335 | 281.9 | 83% |
| 2026-01 | 9 | 4,911 | 1,366,170 | 233,322 | 29,095 | 1,628,586 | 331.6 | 84% |

Key Observations: The best-performing month was September 2024 at 130.5 AED/t (12,388 tons moved). The worst was February 2025 at 1,257.5 AED/t (only 1,282 tons). This 9.6x variation demonstrates the critical impact of voyage density on overall cost efficiency.

# 5. Data Quality and Corrections

## 5.1 ADNOC 225 Contamination (v5.2 Fix)

31 decklog rows from vessel ADNOC 225 (a non-project vessel operating in Saudi Arabia) were identified contaminating the JOPETWIL71 operational data. ADNOC 225 showed average fuel consumption of 2,116 L/day (vs JOPETWIL71’s 299 L/day) and ROB starting at 862,100 liters (vs normal 8,622). These rows were tagged as EXCLUDED_NON_JPT71 in the DL_VESSEL_FLAG column with gray fill formatting. Impact: January 2026 fuel corrected from 65,754L to 154L (−99.8%).

## 5.2 Voyage ID Corrections

- Naming convention break at entry #47: GRM-71 → GRM-J71 transition identified and mapped as aliases

- J71-007 alias: Resolved to correct voyage ID in cross-referencing

- AGU typo fix: Corrected misspelled voyage identifiers

- 2026-12 date typo: December 2026 loading dates corrected to December 2025 in VOYAGE sheet

- BUSHRA exclusion: Non-JPT71 vessel BUSHRA invoices excluded from reconciliation

# 6. ALS Fixed Cost Optimization Scenarios

Three optimization approaches were modeled against the current baseline of 314.67 AED/ton:

## 6.1 Scenario A: Increase Voyage Density

By increasing monthly tonnage throughput while keeping ALS fixed at AED 1.14M/month, the fixed cost dilution effect reduces the blended rate. A +50% increase in monthly tonnage (4,596 → 6,895 t/mo) achieves 256.1 AED/t (−18.6%). This requires no additional investment, only operational scheduling optimization and cargo consolidation.

| Density Increase | Monthly Ton | AED/t | Saving % | Investment |
| --- | --- | --- | --- | --- |
| Baseline (0%) | 4,596 | 338.7 | — | — |
| +20% | 5,516 | 297.4 | -5.5% | 0 AED |
| +50% | 6,895 | 256.1 | -18.6% | 0 AED |
| +100% | 9,193 | 214.8 | -31.7% | 0 AED |

## 6.2 Scenario B: Negotiate ALS Rate Reduction

Negotiating the ALS monthly charter rate downward produces linear cost savings. A 10% reduction (-AED 113,881/month) breaks even against the current blended rate at 313.9 AED/t and saves AED 1.37M annually. A 20% reduction achieves 289.2 AED/t with AED 2.73M annual savings. Leverage points include long-term contract commitment and volume guarantees.

## 6.3 Scenario C: Combined Optimization (Recommended)

Combining density improvement with rate negotiation produces multiplicative benefits. The optimal scenario (Ton +50%, ALS -20%) achieves 223.1 AED/t — a 29.1% reduction from the modeled baseline, with annual ALS savings of AED 2.73M. This represents the Strategic (Long-term) target.

## 6.4 Scenario Comparison Matrix

| Scenario | AED/t | Saving | Annual Δ | Timeline | Grade |
| --- | --- | --- | --- | --- | --- |
| A: Ton +20% | 297.4 | -5.5% | 0 | 1-2 mo | B |
| A: Ton +50% | 256.1 | -18.6% | 0 | 1-2 mo | A |
| B: ALS -10% | 313.9 | -7.9% | 1.37M | 2-4 wk | B |
| B: ALS -20% | 289.2 | -14.6% | 2.73M | 2-4 wk | A |
| C: T+50%, R-20% | 223.1 | -29.1% | 2.73M | 1-3 mo | S |

# 7. Break-Even Analysis

Given the fixed ALS rate of AED 1.14M/month and variable rates (OFCO 81.12 AED/t + GM 9.83 AED/t = 90.95 AED/t variable), the minimum monthly tonnage required to achieve target AED/t rates is:

| Target AED/t | Min Monthly Ton | vs Current Avg | Reqd Voyages | Feasibility |
| --- | --- | --- | --- | --- |
| 300 | 5,448 | 119% | ~10 | Stretch |
| 350 | 4,396 | 96% | ~8 | Realistic |
| 400 | 3,685 | 80% | ~7 | On Track |
| 450 | 3,172 | 69% | ~6 | Easy |

## Idle Month Cost Impact

Each idle month (zero or near-zero tonnage) wastes approximately AED 1.14M in ALS charter costs, adding 13.0 AED/t to the project blended rate when spread across total tonnage. Three idle months would add AED 3.42M and 39.1 AED/t. The February 2025 experience (1,282t, 1,257.5 AED/t) demonstrates this risk in practice.

# 8. Recommendations

- Short-Term (Quick Win): Negotiate ALS charter rate reduction of 10–15%. Leverage: 19-month operational history demonstrating consistent utilization. Target: AED/t below 315 with annual savings of AED 1.37–2.05M.

- Mid-Term (Operational): Optimize voyage scheduling to maintain minimum 5,500t/month throughput (+20% over current average). Focus on cargo consolidation, schedule alignment with loading windows, and minimizing idle periods. Target: AED/t below 300.

- Long-Term (Strategic): Combined Ton+50% density increase with ALS -20% rate negotiation. Target: 223 AED/t (−29% from modeled baseline). Requires both operational excellence and contractual restructuring.

- Critical Guard Rail: Prevent monthly tonnage from falling below 1,300t. Feb 2025 demonstrated that sub-1,300t months cause AED/t to exceed 1,250, destroying 4–5 months of cost efficiency gains. Establish minimum voyage density threshold as a project KPI.

# 9. Report Deliverables

The following files comprise the complete v5.3 analytical package:

| File | Size | Description |
| --- | --- | --- |
| JPT-reconciled_v5.3.xlsx | 969 KB | Master workbook (12 sheets) with all allocations |
| JPT71_ALS_CostOptimization_v5.3.html | 23 KB | Interactive 6-tab scenario analysis dashboard |
| JPT71_Fuel_Loading_Dashboard_v5.2.html | 11 KB | Fuel consumption dashboard (ADNOC 225 corrected) |
| JPT71_Fuel_RootCause_Analysis_v5.2.html | 7 KB | Fuel anomaly root cause analysis |
| JPT71_HVDC_Report_v5.3.docx | — | This report |

End of Report

JPT71 HVDC Project · Samsung C&T / ADNOC · MACHO-GPT v5.3